## Action Plan - BLANK
Iteration 2 Plan
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
revised UCD(5) | shoaib | med |  | 2021-02-05 | 2021-02-24
revised Domain model(5) | masoud | med |  | 2021-02-05 | 2021-02-24
new UCD 1(10) - choose display options | fahad | highest |  | 2021-02-05 | 2021-02-26
new UCD 2(10) - select difficulty | gowtham | highest |  | 2021-02-05 | 2021-02-26
Sequence diagram 1(15) | shoaib | high |  | 2021-02-05 | 2021-02-28
Sequence diagram 2(15) | liam | high |  | 2021-02-05 | 2021-02-28
overall class diagram(10) | masoud | high |  | 2021-02-05 | 2021-02-28
minor release-match to spec(15) | gowtham/fahad | depends on rest |  | 2021-02-05 | 2021-03-02
minor release-quality and clarity(10) | liam/masoud | depends on seq |  | 2021-02-05 | 2021-03-02
MEETING | date
initial review after midterms | 2021-02-21
review 1- completion check of high priority tasks | 2021-02-25
review 2- progress check | 2021-02-28
review 3- check for completion of all tasks + changes/correction | 2021-03-02
final check | 2021-03-04