## Action Plan - BLANK
ACTION PLAN
PROJECT NAME
iteration 4
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
future networking(5) | gowtham | medium | not needed | 2021-03-05 | 2021-03-08
the use of patterns(5) | gowtham | medium | not needed | 2021-03-05 | 2021-03-08
Junit testing(5) | liam | high | completed | 2021-03-05 | 2021-03-08
4a-Final release-correctness(70) | everyone | high | completed | 2021-03-05 | 2021-03-08
4b-Final release-Quality(15) | fahad/liam | medium | completed | 2021-03-05 | 2021-03-10
4c-Final release-Match to spec(20) | masoud/shoaib | high | completed | 2021-03-05 | 2021-03-10
meetings | date |  |  |  |  | communication log
initial review and plan revision(if needed) | 2021-03-21
completion of low prio tasks | 2021-03-23
code work distribution+progress review | 2021-03-26
code review | 2021-03-30
final review/minor changes | 2021-04-03