## Action Plan - BLANK
ACTION PLAN
PROJECT NAME
iteration 4
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
future networking(5) | gowtham | medium | not needed | 2021-03-05 | 2021-04-02 | completed
the use of patterns(5) | gowtham | medium | not needed | 2021-03-05 | 2021-04-02 | completed
Junit testing(5) | liam | high | completed | 2021-03-05 | 2021-04-02 | completed
4a-Final release-correctness(70) | everyone | high | completed | 2021-03-05 | 2021-04-04 | behind schedule
4b-Final release-Quality(15) | fahad/liam | medium | completed | 2021-03-05 | 2021-04-04 | behind schedule
4c-Final release-Match to spec(20) | masoud/shoaib | high | completed | 2021-03-05 | 2021-04-05 | behind schedule
meetings | date |  |  |  |  | communication log
initial review and plan revision(if needed) | 2021-03-21 |  |  |  |  | Meeting was delayed
completion of low prio tasks | 2021-03-23 |  |  |  |  | due to the course load and everyones schedule dates were adjusted
code work distribution+progress review | 2021-03-26 |  |  |  |  | progress discussions
code review | 2021-03-30 |  |  |  |  | code problems were discussed
final review/minor changes | 2021-04-04 |  |  |  |  | no reports